## GOAL1
Goal 1: Provision of Quality Independent Living Services
Goal Description: The Independent Living Network of North Carolina (the incorporated network of eight Centers for Independent Living in North Carolina – hereafter IL Network) provides quality services as needed to remove barriers to independence experienced by people with disabilities in North Carolina.
Objective 1.1: The IL Network staff members are well trained.
|  |  | Funded? | Needed Funds
| What | Who | (Y/N) | 2014 | 2015 | 2016
Activity 1.1.1: IL Network/CIL staff members receive training conducted in compliance with Rehab Act roles and responsibilities. | defn: ensure training received; this goal only focuses on training center's directors/staff
| 1.1.1.1 send individual to ILNet or other Training (airfare, meals, lodging) $16,000 spread out over 3 years | Center Directors |  | 5333.3333 | 5333.3333 | 5333.3333
1.1.1.2
Activity 1.1.2: IL Network/CIL staff members attend conferences and disability related events. | 1.1.2.1 attend NCIL and/or APRIL and/or other conferences and related programs (registration, travel, lodging, meal) $2,000/center = $16,000 | Center Directors and Staff
1.1.2.2
Activity 1.1.3: IL Network/CIL staff members provide cross training opportunities with VR, VRIL, DSB, and other key partners of the NC SILC. | 1.1.3.1 center provides cross training - basic mileage expenses monthly. Current rate .56/mi ; $100/center = $800 | Center staff
1.1.3.2
Objective 1.2: Members of the IL Network implement uniform practices.
Activity 1.2.1: The IL Network Directors or CIL staff leaders participate in at least two (2) face-to-face or teleconference meetings to facilitate network building and the sharing of promising practices each year. | 1.2.1.1 retreats to build network (ex: Nov 2013 retreat) meet at least 2 times (Spring/Fall) mileage at .56/mi ; meals bfast/lunch/dinner; lodging $8,492 | Center Directors and Staff | 0
1.2.1.2
Activity 1.2.2: The IL Network/CIL staff members develop a uniform service delivery manual. | 1.2.2.1 combine development/dissemination printing, duplicating, cost estimate = $300/each x 7 2 centers Sylva/Ashv combined. $2100 estimate. | Center Staff | 0
Activity 1.2.3: The IL Network/CIL staff members disseminate uniform practices and service delivery procedures throughout the Network. | 1.2.3.1 see 1.2.2.1 (combined) | Center Staff | 0

## GOAL2
Goal 2: Leadership and Empowerment of Individuals with Disabilities
Goal Description: Provide services to empower and promote leadership among individuals with disabilities in NC.
|  |  | Funded? | Needed Funds
| What | Who | (Y/N) | 2014 | 2015 | 2016
Objective 2.1: Youth with disabilities are prepared for leadership roles.
Activity 2.1.1: Youth with disabilities participate in a Youth Leadership Forum each year. | One event annually and reported Monthly in P&E; verbally at quarterly SILC; chart completed after YLF |  | Y | 20000 | 20000 | 20000
Activity 2.1.2: Youth with disabilities receive training about Independent Living. | One training session per center per year - $250 * 8 = $2,000 |  | N
Activity 2.1.3: Teachers and parents of youth with disabilities have access to resources concerning independent living and transition experiences. | Add something to websites? |  | N
Objective 2.2: people with disabilities and the community at large are educated on disability policies and regulations on federal, state and local levels.
Activity 2.2.1: People with disabilities participate in training events and conferences. | One presentation per center per year? Cost?? |  | N
Activity 2.2.2: People with disabilities educate the community at large as well as people with disabilities on policies and regulations. | One presentation per center per year? Cost?? |  | N
Activity 2.2.3: People with disabilities provide presentations on Disability History and Awareness, especially in the month of October. | One presentation per center per year? Cost?? |  | N

## GOAL 3
Goal 3: Growth and Improvement of IL Services
Goal Description: Independent Living services in NC are improved and spread throughout the state.
Objective 3.1: Current service areas do not become unserved or underserved to a greater degree, and previously unserved consumers in NC are served.
[5 empty] | Asheville (Disability Partners) |  |  | Charlotte (DR&R) |  |  | Greensboro (Shabazz) |  |  | Greenville (DARC) |  |  | Raleigh (DARA) |  |  | Sylva (DP) |  |  | Wilmington (DRC) |  |  | Winston-Salem (Adaptles)
|  | WHAT | WHO | 2014 | 2015 | 2016 | 2014 | 2015 | 2016 | 2014 | 2015 | 2016 | 2014 | 2015 | 2016 | 2014 | 2015 | 2016 | 2014 | 2015 | 2016 | 2014 | 2015 | 2016 | 2014 | 2015 | 2016
|  | assumption: maintain means reporting what dollars are being received at CILs | Part C from DOE, B goes to DSU | State: $0 |  |  | State: $0 |  |  | State: $0 |  |  | State:$0 |  |  | State: $0 |  |  | State: $0 |  |  | State:$0 |  |  | State: $0
|  |  |  | B: $8,358 |  |  | B: $8,358 |  |  | B: $8,358 |  |  | B: $220,000 |  |  | B: $8,358 |  |  | B: $8,358 |  |  | B: $23,000 |  |  | B: $8,358
|  |  |  | C: $288,435 |  |  | C: $303,881 |  |  | C: $288,435 |  |  | C: $0 |  |  | C: $331,000 |  |  | C: $288,435 |  |  | C: $1,616 |  |  | C:$294,182
Activity 3.1.1: At a minimum, the current level of funding for CILs is maintained, and funding increases are the optimum outcome. | Each center director is constantly networking with other states for funding ideas.
3.1.1.1 Trend funding ; ID trends Q: Is there a minimum level of funding? See 3.2 SPIL. $250K /annually (fed/state funds)
Activity 3.1.2: Part B and Part C CILs maintain financial support from Title VII Part B funding. | See Activity 3.1.1 | 3.1.2.1 plan and be proactive rather than react to the dollars we receive; | CIL Director
3.1.2.2 pursue other streams of income ?
3.1.2.3 explore accessing the Innovation & Expansion (INE) funds
3.1.2.4 what if we have a center to create a virtual center…use website and technology (note: per Julia RSA won't fund this) consider risks and the already committed 2014 funds! Explore ways to leverage technology for underserved unserved - would this help? what can we add to SILC website? Promoted IL on website.
Activity 3.1.3: Information on "How to Start a Center for Independent Living" is provided for the unserved areas of the state. | This info. Cannot be contained in 1 document. Contact info. On how to start a CIL will be put on websites. | 3.1.3.1 ID which counties are underserved due to lack of CIL resources
3.1.3.2 ID counties that do not have CILs
3.1.3.3 develop materials ; disseminate materials/advertise
Activity 3.1.4: The IL Network will include materials on their webpages and social media outlets that can assist consumers both within and outside their service area limits. |  | 3.1.4.1
Activity 3.1.5: The IL Network members will promote IL concepts and distribute useful materials through colleagues and partners that have a statewide focus. | This is an ongoing project of each CIL director. | 3.1.5.1 | CIL's

## GOAT4
Goal 4: Support the Operations of the NCSILC Nonprofit Office
Goal Description: Part B funds are used to ensure that the NC SILC nonprofit office operates efficiently and effectively, in compliance with the Federal Rehabilitation Act, and in accordance with written policies under the Department of Health and Human Services
|  |  | Funded? | Needed Funds
| What | Who | (Y/N) | 2014 | 2015 | 2016
Objective 4.1: Maintain an autonomous and independent NC SILC nonprofit office.
Activity 4.1.1: Part B funds are provided for general operations of the NCSILC non-profit office and the NCSILC related activities. 192,850 | 4.1.1.1 Ensure funds coming in timely ; track reimbursement. Monitor; Report back | SILC Office | Y
Activity 4.1.2: A sub-committee from the SILC identifies and reports annually on best practices from other states by reviewing other SPILs, contacting other SILCs, attending the SILC Congress, and reviewing other publicly-available information. | 4.1.2.1 Research/Study/Contact other offices - identify specifically what you want to find out (metrics?) | Committee/ Sub-Committee (open to others) | 0
| 4.1.2.2 Peer-to-peer mentoring thru APRIL. | Committee/ Sub-Committee (open to others)
Activity 4.1.3: The sub-committee from the SILC contacts other SILC organizations or visits other SILC organizations in the region. | 4.1.3.1 visit other SILC orgs; see also 4.1.2.2 (peer-to-peer mentoring thru APRIL) | Committee/ Sub-Committee (open to others) | 0
Activity 4.1.4: The flow of Title VII, Part B funds (from RSA to the eventual Title VII, Part B contract recipients), shall be transparent, and an accounting of such funds shall be made available by the DSU to NCSILC on a monthly basis. | 4.1.4.1 contract recipients sends SILC office their reports (be cc:'d)… to be informed and help monitor situation (TRACKING) ; this already exists and comes from Kathleen. WHEN Part B funds received …follow entire process..RSA..DVR… recipients. commitee would like to see an email or something to follow. Focus on transparency. | SILC and DSU
4.1.4.2 email request; bank footprint. These may be used to help with tracking.
Objective 4.2: The NC SILC nonprofit office coordinates SPIL-related activities. |  |  | 0
Activity 4.2.1: The NC SILC holds quarterly meetings. | 4.2.1.1 keep track of our meetings |  | 0
| 4.2.1.2 see what we are spending our money on. See expenditures ; finance committee to get this | Finance Committee
Activity 4.2.2: The NC SILC disseminates information. | 4.2.2.1 make sure all information is accessible to members (website; executive directors reports; phone call requests & referrals - chart collection of these calls) | SILC Office | 0
Activity 4.2.3: When sufficient funds remain in a fiscal year, the NC SILC implements an annual IL summit to garner input and monitor implementation of the SPIL. | 4.2.3.1 identify from finance committee (GO/NO-GO decision by March) to see if we have incremental funds available
4.2.3.2 information gathering on how much funds needed (location costs, lodging, travel)
Activity 4.2.4: The NC SILC maintains representation from youth with disabilities. | 4.2.4.1 membership committee tracks membership activity | membership committee
Activity 4.2.5: The NC SILC implements recruitment and membership procedures. | 4.2.5.1 membership committee report-out to SILC | membership committee

## GOAL5
Goal 5: Promote Community Based Living
Goal Description: People with disabilities live in the NC community of their choice.
|  |  | Funded? | Needed Funds
| What | Who | (Y/N) | 2014 | 2015 | 2016
Objective 5.1: Residents in institutions transition to community-based living. |  |  | N
Activity 5.1.1: Part B and C Centers assist consumers with transitions to community-based living. | 5.1.1.1 Assist with one-time transition expenses (personal expenses; buy groceries, utilities, rent) leverage last year's expenses as benchmark: $25,000 per year | CIL | N | 25000 | 25000 | 25000
Activity 5.1.2: The NC SILC maintains a community resource database for transition needs. | 5.1.2.1 leverage databases at each center to track |  | N
Activity 5.1.3: SILRPs (State Independent Living and Rehabilitation Programs), Part B and Part C Centers provide NC SILC with performance data and success stories on deinstitutionalization and transitioning. | 5.1.3.1 |  | N
0
0
0

## GOAL 6
Goal 6: DSUs provide independent services
Goal Description: People with disabilities live in the NC community of their choice.
|  |  | Funded? | Needed Funds
| What | Who | (Y/N) | 2014 | 2015 | 2016
Objective 6.1 people with disabilities have greater access to transportation in their communities |  |  | N
Activity 6.1.1 Partipate in local transportation decision making process |  | CIL | N | 25000 | 25000 | 25000
Objective 6.2 …have supports necessary to live independenty and safely …. |  |  | N
Activity 6.2.1 DSU ..partnership … | 6.2.1.1 DSU reports outlined to follow same method. This will make it easier for our quarterly reporting. | DSUs
N
0
0
0

## Sheet5
Data
OBJECTIVE | ACTIVITY | WHAT | Sum of 2014 | Sum of 2015 | Sum of 2016
3.1 objective - areas don't become unserved or underserved…unserved consumer become served. |  | (blank) |  |  | 4
| Total |  |  |  | 4
| 3.1.1 activity: level of funding is maintained funding is maintained ; increasing is fine too | 3.1.1.1 identify counties that do not have CILs. | 100 | 0 | 0
(blank)
|  | 3.1.2.2 | 5
|  | 3.1.1.2 ID which counties are underserved due to lack of resources - only do ABC | 50 | 0 | 50
|  | 3.1.1.2 ID which counties are underserved due to lack of resources - only do XYZ | 0 | 100 | 0
|  | 3.1.1.2 ID which counties are underserved due to lack of resources - only do EFG | 15 | 12 | 3
| 3.1.1 activity: level of funding is maintained funding is maintained ; increasing is fine too Total |  | 170 | 112 | 53
| 3.1.2 activity: part b & c CILS maintain financial support from title7/partB funding. | 3.1.2.1 assumption: maintain means reporting what dollars are being received at CILs | 40 | 4 | 4
|  | 3.1.2.2 track dollars received/spent | 50 | 4 | 5
|  | 3.1.2.3 dkfjdkfdlkfjd | 10 | 5 | 2
| 3.1.2 activity: part b & c CILS maintain financial support from title7/partB funding. Total |  | 100 | 13 | 11
| 3.1.3 activity: how to start center is provided for unserved areas. | 3.1.3.1 dkjfdk | 11 | 11 | 1
|  | 3.1.3.2 dkfjdkf | 23 | 1 | 2
| 3.1.3 activity: how to start center is provided for unserved areas. Total |  | 34 | 12 | 3
| 3.1.4 activity: IL network will include materials in webpages and social media outlets that can assist consumers. | 3.1.4.1 sldkfjdk |  |  | 3
| 3.1.4 activity: IL network will include materials in webpages and social media outlets that can assist consumers. Total |  |  |  | 3
| 3.1.5 activity: IL network members will promote IL concepts and distribute useful materials thru colleague/partners that have statewide focus | 3.1.5.1 dkfjdkfjd | 55 | 2 | 5
| 3.1.5 activity: IL network members will promote IL concepts and distribute useful materials thru colleague/partners that have statewide focus Total |  | 55 | 2 | 5
| (blank) | (blank)
(blank) Total
3.1 objective - areas don't become unserved or underserved…unserved consumer become served. Total |  |  | 359 | 139 | 79
Grand Total |  |  | 359 | 139 | 79

## order
working session:
goal 1 | start
goal 3 | continue
goal 4 | clarify
goal 5 | no funding | have not allocated funding for transition
goal 2 | on track
goal 6 | on track

## definitions
Unserved area = where CIL doesn't exist
underserved = CIL exists; don't have resources to serve
maintain = track receipt of dollars received/spent